## Goals and Objectives
Goals and Objectives	Where is it covered

Explain with the technical architecture of OSE3.0
Perform a 20 minute demonstration of the use of OSE3.0
Explain how to set up STI build process
Explain how to implement Zones and Regions in multi node environments
Explain how to deploy a POC like environment of OpenShift 3.0
Explain how HA application deployments work in OpenShift 3.0
Explain how to Manage the life cycle of applications in OpenShift 3.0

Module Names	Which Goals are covered
Module 01 : Introduction to Course and Learning Environment
Module 02 : OpenShift 3.0 Architecture
Module 03 : OpenShift 3.0 Installation
Module 04 : Resource Management
Module 05 : The STI Build Method
Module 06 : InstantApps and Tempaltes
Module 07 : Code Lifecycle
Module 08 : Demonstrating OpenShift 3.0 Capabilities

## Sheet2
Task	Module	Details	Hours / Of Effort	Owner	Status
Topic : Welcome to Red Hat GPE Training	Module01	Copied from Fastrax, Needs to be reviewed	0.25	Shachar
Topic : Course Goals	Module01	Copied from Fastrax, Needs to be reviewed	0.25	Shachar
Topic : Course Overview	Module01	Copied from Fastrax, Needs to be reviewed	0.25	Shachar
Topic : Class Environment	Module01	Copied from Fastrax, Needs to be reviewed	0.25	Shachar
Lab : Set Up Your Lab Environment	Module01	Copied from Fastrax, Needs to be reviewed	0.25	Shachar
Topic : Overview and design concepts in OSE3.0	Module02	Copied from Fastrax, Needs to be reviewed and expanded	1	Shachar
Topic : Introduction to Docker	Module02	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Topic : Introduction to Kubernetes Infrastructure	Module02	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Topic : Networking in OSE3.0	Module02	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Topic : Resources overview	Module02	Move into Module04	2	Shachar
Topic : Installation Overview	Module03	Needs to be created - Waiting for GA	2	Shachar	Waiting for GA
Topic : Prepare your Hosts	Module03	Needs to be created - Waiting for GA	2	Shachar	Waiting for GA
Topic : Installation Methods	Module03	Needs to be created - Waiting for GA	2	Shachar	Waiting for GA
Topic : Authentication	Module03	Needs to be created - Waiting for GA	2	Shachar	Waiting for GA
Topic : Web UI	Module03	Needs to be created - Waiting for GA	2	Shachar	Waiting for GA
Topic : Scheduler - Regions and Zones	Module03	Needs to be created - Waiting for GA	2	Shachar	Waiting for GA
Topic : High Availability Deployments.	Module03	Needs to be created - Waiting for GA	3	Shachar	Waiting for GA
Lab : Install OpenShift Using Ansible	Module03	Written for Beta4 - Needs to be reviewed at GA	1	Shachar	Waiting for GA
Lab : Add Nodes	Module03	Written for Beta4 - Needs to be reviewed at GA	1	Shachar	Waiting for GA
Lab : Regions and Zones	Module03	Written for Beta4 - Needs to be reviewed at GA	1	Shachar	Waiting for GA
Lab : Deploy The "Router" and "Registry" Containers	Module03	Written for Beta4 - Needs to be reviewed at GA	1	Shachar	Waiting for GA
Topic : OpenShift Resources	Module04	Needs to be created	2	Shachar
Topic : Projects and Quotas	Module04	Needs to be created	2	Shachar
Topic : Scaling with Replication Controllers	Module04	Needs to be created	2	Shachar
Topic : Services and Routes	Module04	Needs to be created	2	Shachar
Lab : Users, Projects and Quotas	Module04	Written for Beta4 - Needs to be reviewed at GA	1	Shachar
Lab : Services and Routes	Module04	Written for Beta4 - Needs to be reviewed at GA	1	Shachar
Lab : Deployment Configuration and Replication Controllers	Module04	Needs to be created	2	Shachar
Topic : STI Overview	Module05	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Topic : Registry Service	Module05	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Topic : ImageStream	Module05	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Topic : BuildConfig	Module05	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Lab : Deploy an STI Build	Module05	Copied from Fastrax, Needs to be reviewed and expanded	2	Shachar
Lab : Another STI Lab	Module05	Needs to be created	3	Shachar
Topic : Templates Overview	Module06	Needs to be created	2	Shachar
Topic : Using Templates	Module06	Needs to be created	2	Shachar
Topic : Wiring Disparate Components	Module06	Needs to be created	2	Shachar
Topic : Using Templates from the Web Management Console	Module06	Needs to be created	2	Shachar
Lab : Installing a Template	Module06	Needs to be created	2	Shachar
Lab : Wiring Templates together	Module06	Needs to be created	2	Shachar
Topic: Pre and Post deployment Hooks	Module07	Needs to be created	2	Shachar
Topic : Rollback and Activate	Module07	Needs to be created	2	Shachar
Lab : Deployment Hooks	Module07	Needs to be created	2	Shachar
Lab : Rollback	Module07	Needs to be created	2	Shachar
Topic : Demonstrate: Deploy Wordpress using Docker Image. (Builder)	Module08	Needs to be created	2	Shachar
Topic : Demonstrate: Deploy Tiered Application (STI)	Module08	Needs to be created	2	Shachar
Topic : Demonstrate: Deploy EAP Application	Module08	Needs to be created	2	Shachar
Topic : Demonstrate: Deploy FeedHenry Application (Maybe)	Module08	Needs to be created	2	Shachar